## Sheet1
Task | Task1 | Business Driver | Resource | Group | Data | Location | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Project Planning | Planning | Strategic | Project Manager | Management | High | New York | X | X
Requirements Gathering | Analysis | Strategic | Business Analyst | Analysis | Medium | New York |  | X | X
System Design | Design | Technical | System Architect | Design | Medium | San Francisco |  |  | X | X
Development Phase 1 | Development | Technical | Developer Team A | Development | High | San Francisco |  |  |  | X | X | X
Development Phase 2 | Development | Technical | Developer Team B | Development | High | Bangalore | [5 empty] | X | X | X
Testing | QA | Quality | QA Team | Testing | Medium | New York | [7 empty] | X | X
Deployment | Operations | Operational | DevOps | Operations | High | London | [9 empty] | X
Training | Training | Adoption | Trainer | Training | Low | London | [9 empty] | X | X
Documentation | Documentation | Knowledge | Technical Writer | Documentation | Medium | Bangalore | [8 empty] | X | X | X
Post-Launch Review | Review | Improvement | Project Manager | Management | Low | New York | [11 empty] | X